## Sprint Plan
Sprint Plan
ID | Task Name | Start Date | End Date | % Complete | DONE | Notes
S1 | Sprint 1 - Defining Services | 2024-05-06 | 2024-05-10 | 100% | 1
T00 | Create Micro-Service Mapping | 2024-05-06 | 2024-05-08 | 100% | 1 | Define the I/O for each microservice and there relationships.
T01 | Learn About Docker Images | 2024-05-08 | 2024-05-10 | 100% | 1 | Containerizing Programs (Micro-services)
T02 | Make Github Repo | 2024-05-09 | 2024-05-11 | 100% | 1 | Containerizing Programs (Micro-services)
S2 | Sprint 2 - Data Collection | 2024-05-13 | 2024-05-18 | 0% | 0
T02 | Start e-Commerce DataScraper Build | 2024-05-13 | 2024-05-15 | 0% | 0 | Get selling item info: image, price, description, duration from post to sale, etc.
T03 | Factor code for Abitrary API | 2024-05-15 | 2024-05-18 | 0% | 0 | Build abstract base class to ensure simple integration of new e-commerece platforms APIs into the backend.
S3 | Sprint 3 - RAG Service | 2024-05-21 | 2024-05-26 | 0% | 0
| Checkout Minstrel for RAG Capabilities |  |  | 0% | 0
| Checkout RAG Licensing on Models |  |  | 0% | 0
|  |  |  | 0% | 0
S4 | Sprint 4 - RAG |  |  | 0% | 0
0
0

## Backlog
Backlog
ID | T02 | -- | T03
Tasks | Create Datascraper for an e-Commerce Website | Generate Item Descriptions Relavent to Current Market Trends | Abstract API Classes
User Stories | As an AI developer I would like a tool that allows me to easily scrape useful data about items from e-commerece websites. This way I can spend more time worrying about how to train my model instead of trying to find data. | As someone interested in reselling my items, I want a feature that automatically fills in the details needed to capture a buyers attention so I don't to spend tons of time doing that myself. | As someone interested in reselling my items, I want to post my items on as many different e-commerce sites as possible so that my items sell quickly from the time I post them.
| As a market analyst I would like a tool that allows me to easily scrape statistical data and meta data about items. This way I can focus more time and energy on analizing the data, as well as generally have more data to work with. | As someone interested in reselling my items, I want my listing to quickly and effectively capture buyers' attention so that my items sell quickly from the time I post them. | As a developer (especially one new to this programs code) I would like to be able to easily integrate this program with another e-commerce API, if say a new one comes out in the future.
As somone new to reselling items I would like to see some ideas about how to market my items. This way I don't have to spend to much time brainstorming or have to bother someone else for an opinion.
As an artist/entrepreneur I would like a tool that can help me generate ideas for how to market my product (reccomend price, description, etc.) so that my business can be more successful.