## Sprint Plan
Sprint Plan
ID | Task Name | Start Date | End Date | % Complete | DONE | Notes | Column1
S1 | Sprint 1 - Defining Services | 2024-05-06 | 2024-05-10 | 100% | 1
T00 | Create Micro-Service Mapping | 2024-05-06 | 2024-05-08 | 100% | 1 | Define the I/O for each microservice and there relationships. | M
T01 | Learn About Docker Images | 2024-05-08 | 2024-05-10 | 100% | 1 | Containerizing Programs (Micro-services) | M
T02 | Make Github Repo | 2024-05-09 | 2024-05-11 | 100% | 1 | Containerizing Programs (Micro-services) | S
S2 | Sprint 2 - API and RAG Research | 2024-05-13 | 2024-05-18 | 100% | 1
T02 | Start e-Commerce DataScraper Build | 2024-05-13 | 2024-05-15 | 100% | 1 | Get selling item info: image, price, description, duration from post to sale, etc. | H
T03 | Research RAG Pipeline Frameworks and models to use in the RAG Service Pipeline | 2024-05-16 | 2024-05-20 | 100% | 1 | We'll need an image classifier, retrieval model, generative model, and a good framework for setting up the pipeline. | S
S3 | Sprint 3 - Data Collection and RAG Research | 2024-05-21 | 2024-05-28 | 75% | 0
T04 | Factor DataScraper code for Abitrary API Calls | 2024-05-23 | 2024-05-24 | 75% | 0 | Build abstract base class to ensure simple integration of new e-commerece platforms APIs into the backend. | M
T05 | Research and Implement Drivers for parsing HTML/JavaScript for Item Description | 2024-05-26 | 2024-05-28 | 100% | 1 | Regular HTML parsing (like BeautifulSoup) won't work because item descriptions are formatted using JavaScript code at runtime. A browser driver library (Selenium) needs to be used to solve this issue. | H
T06 | Build Database Builder Code | 2024-05-21 | 2024-05-23 | 100% | 1 | Can be just a json file for now, or a SQL database if desired. Should contain information from a broad scope of items. Niche items are super important to have | S
S4 | Sprint 4 - RAG Experimentation | 2024-05-28 | -- | 0%
T06 | Experiment coding a RAG Pipeline | 2024-05-29 | 2024-05-31 | 0% | 0 | Experiment with the RAG in code form. Either by practicing arbitrary techniques or with the proposed pipeline for this project. | H
T07 | Map Out RAG Service Pipeline | 2024-05-31 | 2024-06-01 | 0% | 0 | Have the pipeline of models mapped out, showing the flow of how each component will interact with each other- the specifications of each component- and how/why each component is used (compared to other components that could've been used). | M
T08 | Create List of Keywords to use with the Database Builder Code | 2024-05-28 | 2024-05-28 | 100% | 1 | Idea: Prompt ChatGPT for a list of keywords that will encompass a very broad set of items, creating a robust and varied dataset. | S

## Backlog
Backlog
ID | T02 | -- | T03
Tasks | Create Datascraper for an e-Commerce Website | Generate Item Descriptions Relavent to Current Market Trends | Abstract API Classes
User Stories | As an AI developer I would like a tool that allows me to easily scrape useful data about items from e-commerece websites. This way I can spend more time worrying about how to train my model instead of trying to find data. | As someone interested in reselling my items, I want a feature that automatically fills in the details needed to capture a buyers attention so I don't to spend tons of time doing that myself. | As someone interested in reselling my items, I want to post my items on as many different e-commerce sites as possible so that my items sell quickly from the time I post them.
| As a market analyst I would like a tool that allows me to easily scrape statistical data and meta data about items. This way I can focus more time and energy on analizing the data, as well as generally have more data to work with. | As someone interested in reselling my items, I want my listing to quickly and effectively capture buyers' attention so that my items sell quickly from the time I post them. | As a developer (especially one new to this programs code) I would like to be able to easily integrate this program with another e-commerce API, if say a new one comes out in the future.
As somone new to reselling items I would like to see some ideas about how to market my items. This way I don't have to spend to much time brainstorming or have to bother someone else for an opinion.
As an artist/entrepreneur I would like a tool that can help me generate ideas for how to market my product (reccomend price, description, etc.) so that my business can be more successful.